## Iteration 1
Iteration 1
From: | 2022-10-24
To: | 2022-11-21 | [5 empty] | Please color code the task status | In Progress
Iteration Goals: | Goal 1 | CRUD book (Use Case 4-9) | [5 empty] | Under Testing
| Goal 2 | Project Setup | [5 empty] | Done
| Goal 3 | CI/CD
| Goal 4 | Fix Bugs
(You can specify which use case or functionality or bug to implement/fix in this iteration)
Use Case/Issue | Task | Estimated Effort | Assigned to | Status | Actual Effort
Book CRUD (Use Case 4-9) | Front-end Publisher view | 3 | Bao Nguyen | Done
| Front-end Student view | 3 | Bao Nguyen | Done
| Front-end CRUD for lesson | 3 | Bao Nguyen | Done
| Back-end C,U,D for lesson | 2 | Bao Nguyen | Done
| Front-end component for vocab tab | 1 | Vipul Lade | Done
| Toggle between Chinese/pinyin tab | 3 | Vipul Lade | Done |  | Quynh Helped
| Custom Quill Editor & extract red & yellow words | 3 | Quynh Dong | Done | 3.5
| Add meaning to list of vocab & save to lesson(refer to Dr.Zhang docx and "Vocab" document in DB) | 2 | Vipul Lade | Done
| Display interactive view with the lesson (when user click on red/yellow words, it will shows the meaning/pinyin) - Book Preview | 2 | Quynh Dong | Done | 3
| Back-end lesson itegration(CRUD), vocab integration (create end points for CRUD) | 3 | Quynh Dong | Done | 2.5 | Bao took some parts
Project Setup | Front-end layout for routing and tabs | 2 | Bao Nguyen | Done
| Front-end / Back-end connection | 1 | Quynh Dong | Done | 1.5
| Database - Backend connection | 2 | Quynh Dong | Done | 2
CI/CD | Script can deploy a static webpage on heroku | 2 | Vipul | Done
Fix Bugs | Save vocabs | 1 | Quynh Dong | Done | 1
| Toggle vocabs in Book | 1.5 | Quynh Dong | Done | 1.5
| Add Lesson button in Lesson CRUD( publisher view) | 0.5 | Bao Nguyen | Done
| Tab component center align | 0.5 | Bao Nguyen | Done
| QuillEditor binding content | 0.5 | Bao Nguyen | Done

## Iteration 2
Iteration 2
From: | 2022-12-19
To: | 2022-01-09 |  |  |  |  | Please color code the task status | In Progress
Iteration Goals: | Goal 1 | CRUD Assignment (Use Case 10-11) |  |  |  |  | Under Testing
| Goal 2 | Login/Sign-up; Join Section |  |  |  |  | Done
| Goal 3 | Students do homework/ Grading/ Feedback (comment)
| Goal 4 | Iteration I continues & Bugs Fixed
| Goal 5 | Discussion board
(You can specify which use case or functionality or bug to implement/fix in this iteration)
Use Case/Issue | Task | Estimated Effort | Assigned to | Status | Actual Effort
CRUD Assignment (Use Case 10-11) | Back-end CRUD for Questions | 3 | Chase Lennartson | Done
| Back-end CRUD for Homework | 3 | Chase Lennartson | Done
| Publisher creates Question bank for each lesson | 2 | Quynh Dong | Done
| Teacher creates question bank for each lesson | 3 | Quynh Dong | Done
| Teacher can choose questions from question bank and assign point to them | 4 | Quynh Dong | Done
| Teacher can CRUD an Assignment | 3 | Quynh Dong | Done
CRUD Exam | Teacher create exam wtih questions and time setting | 3 | Quynh Dong | Done
Login/Signup/Join section (Use Case 1-3) | Login/Signup | 3 | Bao Nguyen | Done
| Undirected connect MongoDB with Auth0 | 3 | Bao Nguyen | Done
| Authentication | 3 | Bao Nguyen | Done
| Authority (publisher/teacher/student) | 3 | Bao Nguyen | Done
| Teacher creates Section | 1 | Quynh Dong | Done
| Student joins Section (front-end back-end) | 2 | Bao Nguyen | Done
| Validation when user join section | 1 | Bao Nguyen | Done
| Teacher can see section student list | 2 | Bao Nguyen | Done
| Teacher can request approval |  | Bao Nguyen | Done
| User can view and edit profile | 3 | Chase Lennartson | Done
User's action | Publisher can view/accept list of user request for teacher role | 2 | Bao nguyen | Done
| User(teacher) can request teacher role | 1 | Bao Nguyen | Done
| Back-end CRUD for User | 3 | Bao Nguyen | Done
| Back-end CRUD for Section | 3 | Quynh Dong, Bao Nguyen | Done
Students do homework/ Grading/ Feedback (comment) (Use Case 12-14) | Audio Storage | 3 | Quynh Dong | Done
| Back-end CRUD for answer | 4 | Quynh Dong | Done
| Back-end CRUD for comment | 2 | Quynh Dong | Done
| Teacher/Student can answer | 2 | Quynh Dong | Done
| Teacher/Student can comment | 2 | Quynh Dong | Done
| Back-end CRUD for Exam | 3 | Quynh Dong | Done
| Student can do exam and submit | 4 | Quynh Dong | Done
| Teacher can grade exam submission | 4 | Quynh Dong | Done
Discussion Board | User can create a Discussion | 2 | Bao Nguyen | Done
| User can give answer to a Discussion | 3 | Bao Nguyen | Done
Iteration I continues | Front-end component for Grammar tab | 3 | Vipul Lade | Done
| Back-end CRUD for grammar | 3 | Vipul Lade | Done
| Pop up feature for Grammar | 3 | Vipul Lade | Done
Fix Bugs/ Additional Modification | Save Lesson have duplicated values for different type after re-save | 2 | Quynh Dong | Done
| Fixing Callback not display (Log in) | 1 | Bao Nguyen | Done
| Publisher can create Pre-defined assignment | 3 | Quynh Dong | Done
| Teacher can create assignment/exam | 2 | Quynh Dong | Done
User can sort answers by name, time
| Drag and Drop for Publisher to modify question order |  | Bao Nguyen | Done
| Publisher can record for each sentence |  | Vipul Lade